## Ideal
Event name
Timeline |  | Event date
Event City/PR
Date | Task | Assigned to | Staus
March (2-2.5 years prior to event) | Deadline to submit proposal to host the conference to CEEA-ACEG head office
April (2-2.5 years prior to event) | Proposals reviewed and accepted
Establish team/committee leads
Begin brainstorming ideas for speakers, entertainment, activitites and suppliers
June (at conference 2 years before the evnet) | Host publicly announced
1-2 years prior to the event | Establish necessary Sub-Committee leads and team members
Reserve potential rental spaces
Reserve services of outside suppliers including keynote speakers
Create sponosor package for Board review
Approach sponsors for support
| Research accomodations & negotiate group rates | CEEA-ACEG Board
September-October (prior to event) | Update all speaker forms (ex. Releases, travel, housing, audiovisual). | and Conference committee
Purchase Oxford Abstract (or other software) subscription
Update committee contact list for website posting
Confirm sponsors, gather logos for website
Create event description outlining theme
Release call for papers
February-March | Review submissions and notify authors of results
Confirm speakers, finalize program & schedule
Gather Sponsor bios and logos
Update registration with fee structure. Make sure to include cancellation policy.
Review budget and adjust if needed
| Update Website with event information | CEEA-ACEG Board
Create online registration - once program is complete
| Send deposits to outside suppliers, unless already done (ex. Decorator, security, official airline and car rental, audiovisual, entertainment, registration services). | CEEA-ACEG Board
March | Online registration live | CEEA-ACEG Board
Determine audio-visual needs for each concurrent session based on speaker agreements
April 1 | Determine and order awards & speaker gifts | CEEA-ACEG Board
Prepare master schedule of all known printing requirements to include specific items, anticipated quantity, deadlines, and potential printers.
Review and update venue function-space assignments and communicate to venue.
Confirm all sponsor invoice have been sent & paid
Begin registration reports to committee (weekly or bi-weekly based on committee preference)
| Purchase lanyards for name tags | CEEA-ACEG Board
| Review of signage requirements and design | CEEA-ACEG Board
| Develop on-site delegate packages | CEEA-ACEG Board
Review conference evaluation forms
May | Begin all food and beverage menu selections.
| Order all on-site office equipment. | CEEA-ACEG Board
Identify and assign staff's on-site responsibilities..
Confirm details and needs of sponsors
Finalize details with outside suppliers
Adjust website as needed
Early June | Review budget, and adjust as required.
| Prepare evaluation forms for speakers, delegates, exhibitors, etc. | CEEA-ACEG Board
1 - 2 Weeks Prior | Finalize all food and beverage selections.
| Finalize venue and AV requirements | CEEA-ACEG Board
Begin preparation of registration packets.
Provide required guarantees to venue.
During | Receive all shipments, equipment, and supplies.
Set up onsite offices & inforamtion table
Confirm and monitor pickup of all rental equipment and supplies.
Arrange for return shipment of materials.
Coordinate ongoing details/issues with venues
3 Weeks Post | Send all thank-you letters.
Prepare summary report(s) of all evaluation forms.
Finalize report documents and distribute,

## 2012
Manitoba Planning Conference Critical Path
Month to be completed | Task | Personnel Assignment | Staus
ASAP
| Establish necessary Sub-Committee leads and team members | Steering Committee | complete
| Prepare and forward a tentative event schedule to venue. | Strauss | complete
| Begin recruiting speakers, entertainment etc. | Program Committee | complete
| Confirm Program speakers, finalize program & event schedule | Program Committee | in progress
| Establish registration-fee structures and policies. Make sure cancellation procedures are included. | Chair/Strauss/Contact | complete
| Finalize event budget based on program needs | Strauss/Accountant | in progress
| Update all speaker forms (ex. Releases, travel, housing, audiovisual). | Strauss | na
| Sponsor Prospectus Prepared & list developed / confirmed | Sponsorship Committee | in progress
| Sponsor package created and published to website | Sponsorship Committee/Strauss | in progress
| Update Website with event information | Strauss | complete
| Send Save the date email and other communications as necessary | Steering Committee | complete
| Create online registration - once program is complete | Strauss | complete
| Identify areas of need for outside suppliers; outline specific requirements, and begin selection (ex. Decorator, security, official airline and car rental, audiovisual, entertainment, registration services). | Strauss | in progress
| Online registration live | Strauss | complete
| Establish transportation needs, confirm with supplier | Steering Committee/Strauss | in progress
| Establish procedures and controls forevent admittance via tickets or badges. *Establish monitoring process. | Strauss | in progress
| Follow up with speakers and begin booking travel if necessary | Program Committee/Strauss | in progress
| Gather Sponsor bios and logos | Strauss | in progress
January 2013 | Begin designing event printed program | Strauss | in progress
| Determine audio-visual needs for each concurrent session based on speaker agreements | Strauss | in progress
| Promote event in identified professional publications. | Steering Committee | in progress
| Determine and order speaker gifts | Steering Committee/Strauss | complete
| Prepare master schedule of all known printing requirements to include specific items, anticipated quantity, deadlines, and potential printers. | Strauss | complete
| Review and update venue function-space assignments and communicate to venue. | Strauss | complete
| Begin processing registration forms as received. | Strauss | complete
| Begin registration reports to committee (weekly or bi-weekly based on committee preference) | Strauss | complete
| Review of signage requirements and design | Strauss | complete
| Develop on-site delegate packages | Steering Committee | in progress
by Jan 22 | Review conference evaluation forms | Steering Committee | complete
| Begin all food and beverage menu selections. | Strauss/Contact | complete
| Order all on-site office equipment. | Strauss | complete
| Identify and assign Strauss staff on-site responsibilities. | Strauss | complete
| Confirm details and needs of sponsors | Strauss | in progress
| Design delegate namebadges | Strauss | complete
by Feb 1 | Finalize details with outside suppliers | Strauss | in progress
| Review hotel sleeping-room pickup. | Strauss/Steering Committee | in progress
| Print Program | Strauss
| Review budget, and adjust as required. | Steering Committee | in progress
| Prepare evaluation forms. (speakers, delegates, exhibitors) | Strauss | in progress
| Receive all bios and notes necessary for moderators | Programm Committee to Strauss | in progress
by Feb 12 | Finalize all food and beverage selections. | Strauss | in progress
| Finalize and mail detailed requirements to venue and all on-site suppliers. | Strauss | in progress
| Comfirm arrangements for all staff and VIP travel and housing. | Strauss | in progress
by Feb 19 | Finalize on-site accounting requirements (e.g., on-site payments, deposits, cash-out procedures). | Strauss/Steering Committee | in progress
| Begin preparation of registration packets. | Strauss
| Communicate all last-minute changes and new requirements to hotel and affected suppliers. | Strauss
by Feb 22 | Provide required early guarantees to venue. | Strauss
| Complete proofing of badges and preparation of packets. | Strauss
| Verify VIP arrivals and schedule airport pick-up. | Strauss/Program Committee
on Feb 25 | Pack and send all event materials for early shipment. | Strauss
| Prepare and print preregistrant list. | Strauss
Coordination Phase On-Site | Receive all shipments, equipment, and supplies. | Venue
| Set up onsite offices. | Strauss
| Confirm and monitor pickup of all rental equipment and supplies. | Strauss
| Arrange for return shipment of materials. | Strauss
Evaluation Phase 2-3 Weeks Post Event | Prepare list and mail all thank-you letters. | Strauss
| Collect and organize data for final event reports. | Strauss
| Obtain evaluations from event support personnel (staff, volunteers, consultants). | Strauss
| Prepare summary report(s) of all evaluation forms. | Strauss
| Prepare final report | Strauss
Evaluation Phase 1 Week Post Event | Finalize report documents and distribute, | Strauss/Steering Committee